## Tasks
AGIC Conference 2020
Planning/Action Items | 2020-08-20
Task: | Assigned to: | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Conf | Post | Notes
COMMITTEE COORDINATION & MEETING OPERATION
Organize Conference Committee |  | Dec: Due; Notes: Maintain membership and status
Schedule committee meetings |  | Dec: Done; Notes: 3rd Thursday of every month.
BUDGET
Establish a State Lands Purchase Order |  | Dec: Done
Establish fees |  | Jan: Done; Notes: $3,000 - Platinum conference sponsor $2,200 - Gold conference sponsor $1,700 - Silver conference sponsor $900 - Bronze conference sponsor +$300 - +Tuesday, set up in ballroom for sponsor +$400 - +Tuesday, set up in in ballroom and table in room for sponsor +$450 - Tuesday only for sponsor +$100 - T-shirt logo for Silver sponsor +$200 - T-shirt logo for Bronze sponsor +$100 - Program advertisement for Silver sponsor $500 - Luncheon or social sponsor $250 - Breakfast or break sponsor $250 - Program advertisement $250 - Student scholarship $100 - Literature insert $325 - 4-day Attendee - Early bird $350 - 4-day Attendee $160 - 4-day Student $250 - 3-day Attendee - Early bird $275 - 3-day Attendee $120 - 3-day Student $165 - Attendee, Day - Early bird $190 - Attendee, Day $50 - Student, Day
Setup & monitor budget | Ongoing | Notes: Realistically expect 200 attendees and 20 exhibitors. PO (x) has been cut for ~$xK.
Monitor registration payments | Ongoing | bar: Dec; Notes
Coordinate with AGIC treasurer |  | Post: Due; Notes: Evaluate conference proceeds
Credit Card Processing |  | Mar: Due; Notes: Implement process for credit card payments
VENUE COORDINATION
Coordinate with the meeting planners |  | Jan: Done; Notes: Establish a contract with the venue, and expo company; Determine credit card processing source
Choose venue |  | Jan: Done
Set conference dates |  | Dec: Done; Notes: August 25-28, with setup on 24th; Take into consideration Federal fiscal year, NSGIC conference, SWUC, etc.
Acquire venue costs |  | Feb: Due; Notes: Meeting room fees, A/V fees, Food & Beverage costs
Develop room layouts |  | Jul: Due; Notes: Ballroom layout Presentation room seating Presentation room table/lectern Computer labs Electrical Internet Audio Easels
Hospitality room |  | Jun: Due; Jul: Due; Notes: Arrange guest rooms in the vicinity
Food & Beverage (F&B) - set menu |  | Jun: Due; Jul: Due
F&B - provide meal/break counts |  | Aug: Due; Sep: Due
Review and approve Banquet Event Order (BEO) |  | Jul: Due; Aug: Due
WEBSITE |  | Notes: http://agicsymposium.org/
Establish the site for the upcoming conference |  | Jan: Done
Set up the registration database |  | Feb: Due; Mar: Due
Set up payment mechanism(s) |  | Feb: Due; Mar: Due
Open registration |  | May: Due; Jun: Due
Set up call for presentations, technical sessions, and hands-on workshops |  | Mar: Due; Apr: Due
Set up call for sponsorship |  | Mar: Due; Apr: Due
Set up call for maps & apps |  | May: Due; Jun: Due
Set up call for volunteer of the year award |  | May: Due; Jun: Due
Set up call for student scholarship application |  | Feb: Due; Mar: Due
Monitor registrations | Ongoing
Update website data | Ongoing | Notes: Keynote/lunch speakers, agenda, additional sponsor logos
AGENDA & SPEAKER COORDINATION
Secure keynote speaker |  | Jan: Due; Feb: Due
Layout agenda presentation slots |  | Feb: Due; Mar: Due; Notes: Start at 10:00 a.m. on Wednesday.
Call for presentations/technical sessions/workshops |  | Mar: Due
Review presentation and workshop submittals |  | Apr: Due; May: Due
Fill in agenda presentations and workshops |  | Apr: Due; May: Due; Notes: Include lightning rounds. No AGIC meeting.
Send draft agenda to presenters |  | May: Due; Jun: Due
Finalize agenda |  | May: Due; Jun: Due
Collect presenter bios |  | Jun: Due; Jul: Due; Notes: Part of the submittal process
Solicit for special A/V needs |  | Jun: Due; Jul: Due
Address special A/V needs for presenters |  | Aug: Due; Sep: Due
Arrange for presentation computers |  | Jun: Due; Jul: Due; Notes: Pima County will supply
Copy and arrange presentation slides on the computers |  | Aug: Due; Sep: Due
Assign session moderators |  | Jul: Due; Aug: Due
Create/Print Room Signs |  | Jul: Due; Aug: Due; Notes: Provide hotel with marquee content
Create/Print Certificates |  | Jul: Due; Aug: Due; Notes: Speakers, ???
Post presentations to the website |  | Post: Due
EXHIBITOR/SPONSOR COORDINATION
Secure Expo Company through the meeting planners |  | Jan: Due
Brainstorm exhibitors/sponsors |  | Jan: Due
Create/update contact list |  | Jan: Due
Develop at-a-glance sponsorship table |  | Jan: Due
Develop form letter for solicitation |  | Jan: Due
Develop exhibitor packet for the website |  | Feb: Due; Mar: Due
E-mail exhibitor announcement |  | Feb: Due; Mar: Due
Send 2nd e-mail announcement |  | Apr: Due; May: Due
Solicit for lunch, break, social sponsorship |  | Apr: Due; May: Due
Map exhibitor locations |  | Jul: Due; Aug: Due
Solicit for raffle donations |  | Jul: Due; Aug: Due
Solicit for hospitality suite sponsors |  | Jul: Due; Aug: Due
Track sponsorship payments | Ongoing
MATERIALS & MAIL-OUTS
Develop and send 1st e-mail announcement |  | Jan: Done
Email montly notice |  | Done | Done | Due | Due | Due | Due | Due | Due | Due | Due |  |  | When agenda is finalized. Include reminder on hotel room expiration.
Reach out to rural communities |  | Mar: Due; Apr: Due
Marketing - Notify websites and other media |  | Mar: Due; Apr: Due
Facebook page |  | Mar: Due; Apr: Due
REGISTRATION
Set early bird dates |  | Jan: Done; Feb: Due; Notes: Set to Friday ~1 month prior: July 24th
Establish credit card processing logistics |  | Apr: Due; May: Due; Notes: On-site registration
Assign registration timeslots |  | Jul: Due; Aug: Due
Inventory registration supplies |  | Jun: Due; Jul: Due; Notes: Laptop, printer, paper, color paper?
Oversee on-site registration |  | Conf: Due
MAPS & APPS CHALLENGE
Develop contest criteria |  | Mar: Due; Notes: Pending survey results
Announce call for Maps & Apps |  | Jun: Due; Notes: Web/mobile app category included.
Coordinate poster display racks |  | Aug: Due
Create info cards |  | Aug: Due
Coordinate with the mobile app |  | Aug: Due
Develop slide show |  | Sep: Due
Develop Maps & Apps ballot |  | Sep: Due
Oversee on-site logistics |  | Conf: Due
AWARDS
Certificates for presenters and workshop teachers |  | Sep: Due
Volunteer of the year |  | Aug: Due
Other special recognitions |  | Sep: Due
PRINTING
Presentation room signs |  | Aug: Due
Certificates for presenters and workshop teachers |  | Aug: Due
Certificates for Maps & Apps winners |  | Conf: Due
Conference signage |  | Aug: Due; Notes: Welcome, registration, sponsors, social, luncheon, breaks
Name badges |  | Sep: Due
Attendee list |  | Sep: Due
Vegetarian meal tickets |  | Sep: Due
Social flyer |  | Aug: Due
Mobile app flyer |  | Aug: Due
COMPUTER LABS
Coordinate hands-on lab 1 |  | Jan: Done; Notes: Pima County training laptops
Coordinate hands-on lab 2 |  | Jan: Due; Notes: TeachMeGIS?
CONFERENCE PROGRAM
Design program cover page |  | Jun: Due
Coordinate the welcome letter |  | Jul: Due; Notes: Authored by the current AGIC chairperson
Ads |  | Jul: Due
Collect abstracts and bios |  | Aug: Due
Acquire hotel map |  | Aug: Due
Layout the program |  | Aug: Due
Coordinate printing |  | Aug: Due; Notes: Due to printer by August ???; print 300 or 325?
T-shirts
Design t-shirt |  | Jul: Due
Coordinate printing |  | Aug: Due
ATTENDEE PACKET/SUPPLIES
Inventory supplies |  | Feb: Due
Order name tag stock |  | May: Due
Order name tag holders |  | May: Due; Notes: Lanyard style
Order lanyards |  | May: Due
Order ribbons for name badges |  | May: Due
Solicit for bags |  | May: Due; Notes: Purchase
Maps & Apps ballot |  | Aug: Due
Social flyer |  | Aug: Due; Notes: Kayaking
Moblie app flyer |  | Aug: Due
Other notices |  | Aug: Due
Map of the host town |  | Aug: Due
Stuff bags |  | Sep: Due
Assemble name badges |  | Conf: Due
Mobile app |  | Mar: Due; Notes: MobileUp
SOCIAL EVENTS
Wednesday night event |  | Mar: Due; Notes: Maps & Apps Gallery
Thursday night event |  | Mar: Due; Notes: At the venue.
Friday afternoon Watson Lake |  | Jun: Due; Notes: Kayaking
GENERAL
Transport materials to hotel |  | Conf: Due
Set up for conference at hotel |  | Conf: Due
Tear down at hotel |  | Conf: Due
Sponsor sign person |  | Sep: Due
Job Board |  | Conf: Due
Solicit for volunteer of the year |  | May: Due
Coordinate and print signage |  | Aug: Due
Coordinate easels for posters and signage |  | Sep: Due; Notes: Rent from the venue.
Coordinate scholarships for students |  | Feb: Due
Online survey |  | Post: Due

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only